## in
Card ID | Card Name | Card URL | Card Description | Labels | Members | Due Date | Attachment Count | Attachment Links | Checklist Item Total Count | Checklist Item Completed Count | Vote Count | Comment Count | Last Activity Date | List ID | List Name | Board ID | Board Name | Archived | Start Date | Due Complete
634d7788240e800072adde34 | UI Design | https://trello.com/c/Qhi3muoO/19-ui-design | This tasks should content our ui mockups and prototype designed using invision. |  | chimuanyaibecheozor1 | 2022-10-26T21:39:00.000Z | 19 | https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec28769bac401cd7093f2/download/index_html.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec28a7315d60562308bc9/download/index_pop_up_1.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec28c2efd23014e42a31b/download/index_pop_up_2.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec28fea194800b5748b5c/download/index_pop_up_3.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29137c7d7001dc18ad1/download/index_pop_up_4.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29367d5f100404f6aca/download/index_search_bar_query_result_available.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29686097a0212cc36f7/download/my_booking_page_unsuccessful_ref_code.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29815faa701e007752b/download/my_booking_page.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29a7a1d25002300c993/download/payment_confirmation.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29b61baa10036387299/download/payment_confirmed.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29d0dcefe00a61d110b/download/payment_form.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec29e74ab4400672d68d6/download/popup_room_available_1.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec2a033461f04598f60e0/download/popup_room_available_2.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec2a2f96aa500160a608f/download/popup_room_available_3.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec2a330fac001c5cb636b/download/popup_room_available_4.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ec2a5d64f6604d0bb91d4/download/popup_room_unavailable_7.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/636ecc884a84a5035e147de0/download/index_search_bar_query_result_unavaible.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/63716773720b3c019cb9df9d/download/index_search_bar_to_booking.png, https://trello.com/1/cards/634d7788240e800072adde34/attachments/637167794d4fa101ffa3d63a/download/Room_details_-_pop_up_(to_booking).png | 0 | 0 | 0 | 7 | 2022-12-09T08:44:00.935Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
6343368d351a4d00a77c913f | . | https://trello.com/c/qt8uaa7m/5-untitled |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-09T21:01:06.861Z | 634330e1f5185f0146e485fe | Design | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63597b85942745045ae8d328 | Textual & Sequence Diagram - Check In | https://trello.com/c/NnLWkKy3/50-textual-sequence-diagram-check-in |  | (yellow) | chimuanyaibecheozor1, kyokoyamasaki | 2022-11-02T14:00:00.000Z | 1 | https://trello.com/1/cards/63597b85942745045ae8d328/attachments/637cb0b6bbad040023f20a4e/download/Textural_%26_sequence-check-in.pdf | 0 | 0 | 0 | 1 | 2022-12-09T08:36:01.296Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
63597bce633fe901951a6042 | Textual & Sequence Diagram - Check Out | https://trello.com/c/xSEfWG61/51-textual-sequence-diagram-check-out |  | (yellow) | chimuanyaibecheozor1, kyokoyamasaki | 2022-11-02T14:00:00.000Z | 1 | https://trello.com/1/cards/63597bce633fe901951a6042/attachments/637cb0ecae194800ec05224e/download/textural%26sequence-check-out_2.pdf | 0 | 0 | 0 | 1 | 2022-11-22T13:56:35.459Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
634d76c3e4316000916db51d | Personas | https://trello.com/c/CDrrqcUD/15-personas |  |  | muhammadhajijamel | 2022-10-23T21:39:00.000Z | 2 | https://trello.com/1/cards/634d76c3e4316000916db51d/attachments/6355cc517a52f90068e7d2f8/download/Web_app_persona1-01.png, https://trello.com/1/cards/634d76c3e4316000916db51d/attachments/6355cc53bd880c00bccd1928/download/Web_app_persona1-02.png | 4 | 2 | 0 | 0 | 2022-11-15T13:04:53.752Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634d76c8abd9aa0024fc14f2 | MOSCOW | https://trello.com/c/U6US6Bnd/16-moscow |  |  | kyokoyamasaki, rayaanchowdhury2 | 2022-10-21T21:39:00.000Z | 1 | https://trello.com/1/cards/634d76c8abd9aa0024fc14f2/attachments/634ebd6626f2eb03f536fa0e/download/MoSCoW.pptx | 0 | 0 | 0 | 0 | 2022-11-15T13:04:58.394Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
634d76d6b36da2007868614e | Empathy Map | https://trello.com/c/k5HMPdDL/17-empathy-map |  |  | kyokoyamasaki | 2022-10-24T15:30:00.000Z | 2 | https://trello.com/1/cards/634d76d6b36da2007868614e/attachments/634ebd4bd7e5c405a836599d/download/Empathy_map_for_Emma_%26_John.pptx, https://trello.com/1/cards/634d76d6b36da2007868614e/attachments/635404834eef77002418d92e/download/rev.Empathy_map_for_Emma_%26_John.pdf | 0 | 0 | 0 | 0 | 2022-11-15T13:05:01.048Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
634d76bbcb50190038d97a09 | Use-case Diagram | https://trello.com/c/jSA1WOMx/14-use-case-diagram |  |  | muhammadhajijamel | 2022-10-21T21:39:00.000Z | 2 | https://trello.com/1/cards/634d76bbcb50190038d97a09/attachments/6353f62300d371037a29b5cb/download/HOTEL_USE_CASE.png, https://trello.com/1/cards/634d76bbcb50190038d97a09/attachments/6368d21b098a8000ec2c2cf3/download/HOTEL_USE_CASE_2.png | 0 | 0 | 0 | 1 | 2022-11-15T13:05:22.558Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
63597bd23358d60102a7f12f | Textual & Sequence Diagram - Cleaner Room Status | https://trello.com/c/CzpCpPvu/52-textual-sequence-diagram-cleaner-room-status |  |  | muhammadhajijamel | 2022-11-02T14:00:00.000Z | 2 | https://trello.com/1/cards/63597bd23358d60102a7f12f/attachments/6368d5c596ab0d00d25d1e93/download/Web_Dev_Assessment_1_-_Text_Cleaning.pdf, https://trello.com/1/cards/63597bd23358d60102a7f12f/attachments/6368dc548c50760059e11b96/download/Sequence_-_Cleaning.png | 0 | 0 | 0 | 0 | 2022-11-15T19:51:45.114Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
63597b547e519e0320e2f1d2 | Textual & Sequence Diagram - Bookings | https://trello.com/c/ilbdzpfT/48-textual-sequence-diagram-bookings |  |  | rayaanchowdhury2 | 2022-11-02T14:00:00.000Z | 2 | https://trello.com/1/cards/63597b547e519e0320e2f1d2/attachments/6372d330ad96ca06abd95365/download/BookingSequence.jpg, https://trello.com/1/cards/63597b547e519e0320e2f1d2/attachments/6372d3372a38a100e48b93bc/download/Text_case.jpg | 0 | 0 | 0 | 0 | 2022-11-15T19:51:46.252Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
63597b5d1c3cf000a0bf3c1c | Textual & Sequence Diagram - Hotel Details | https://trello.com/c/laEqQbVQ/49-textual-sequence-diagram-hotel-details |  |  | kyokoyamasaki | 2022-11-02T14:00:00.000Z | 6 | https://trello.com/1/cards/63597b5d1c3cf000a0bf3c1c/attachments/63626c4bd5b0df00f23e5da7/download/1-hotel-details.pdf, https://trello.com/1/cards/63597b5d1c3cf000a0bf3c1c/attachments/63626cc7010312001587a9f4/download/2-Browse-rooms.pdf, https://trello.com/1/cards/63597b5d1c3cf000a0bf3c1c/attachments/63626cd3b66ee8026bfd5ab0/download/3-Browse-facilities.pdf, https://trello.com/1/cards/63597b5d1c3cf000a0bf3c1c/attachments/63626ce3a1e4e9022e851d8c/download/4-Browse-attractions.pdf, https://trello.com/1/cards/63597b5d1c3cf000a0bf3c1c/attachments/63626cf3de990a064e0adf18/download/5-Browse-contact.pdf, https://trello.com/1/cards/63597b5d1c3cf000a0bf3c1c/attachments/63626cfc5a184400bbbbc54e/download/6-Browse-location.pdf | 0 | 0 | 0 | 0 | 2022-11-15T19:51:47.662Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
634d77c26e33a104b0272c50 | Source free images | https://trello.com/c/AsIx5wMv/20-source-free-images |  |  | kyokoyamasaki, rayaanchowdhury2 | 2022-10-21T21:39:00.000Z | 0 |  | 0 | 0 | 0 | 1 | 2022-11-15T13:05:03.944Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
637397532330ec04caafcc04 | ASSESSMENT DEADLINE | https://trello.com/c/VlmSLj8j/89-assessment-deadline |  |  |  | 2022-12-09T15:00:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-11-15T13:42:43.582Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637397942e282500511b5982 | SPRINT 3 | https://trello.com/c/8goxXZSS/90-sprint-3 |  |  |  | 2022-11-22T12:00:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-12-08T14:56:56.248Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE | 2022-11-15T13:43:15.796Z | FALSE
637397ec5d024602345a9723 | RESEARCH METHODS DEADLINE | https://trello.com/c/z1T0r1HF/91-research-methods-deadline |  |  |  | 2022-11-30T13:44:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-12-08T14:56:59.458Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
63739813dddbad0263cec959 | DATABASE MANIPULATION DEADLINE | https://trello.com/c/Ad9MGRJ5/92-database-manipulation-deadline |  |  |  | 2022-12-05T15:00:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-12-08T14:57:07.534Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
637398547e3bb4053a0f0b86 | FINAL SPRINT | https://trello.com/c/PXF3u4hQ/93-final-sprint |  |  |  | 2022-12-08T11:59:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-12-08T18:14:35.874Z | 63738e25119e5801f75b0ee6 | Guides/ References | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE | 2022-12-06T08:00:00.000Z | FALSE
6357303a0d596901e7ab78b3 | BackLog | https://trello.com/c/y9hi7K1A/32-backlog | A list of the things we think we want to do, maybe not quite ready for work, but high likelihood of being worked on. This is the staging area where specs should get fleshed out. No limit on the list size, but we should reconsider if it gets long. |  |  |  | 1 | https://trello.com/1/cards/6357303a0d596901e7ab78b3/attachments/6357305b1d740b0219163c52/download/Backlog.png | 0 | 0 | 0 | 0 | 2022-10-25T00:41:56.205Z | 634334a6236818033cf95cbf | Front End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
635974f5bdf77e05a1c4088e | User Story | https://trello.com/c/8a7rpn9t/47-user-story |  |  | chimuanyaibecheozor1, kyokoyamasaki, muhammadhajijamel, rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-11-15T13:40:32.486Z | 634334a6236818033cf95cbf | Front End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634bd4f042d34d03aa118669 | Inquire about payment handling | https://trello.com/c/aZ4r9fQL/11-inquire-about-payment-handling |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T21:24:28.750Z | 634334a6236818033cf95cbf | Front End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
6373869c7d74f501eaffc307 | 4 | https://trello.com/c/YaqUShaQ/65-4 |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-11-15T12:38:25.870Z | 634334a6236818033cf95cbf | Front End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
637398f839e817029c8f27b3 | BackLog | https://trello.com/c/Ua44f2KC/94-backlog | A list of the things we think we want to do, maybe not quite ready for work, but high likelihood of being worked on. This is the staging area where specs should get fleshed out. No limit on the list size, but we should reconsider if it gets long. |  |  |  | 1 | https://trello.com/1/cards/637398f839e817029c8f27b3/attachments/637398f939e817029c8f27d7/download/Backlog.png | 0 | 0 | 0 | 0 | 2022-11-15T13:49:45.494Z | 63739497c66e9803912c48cb | Back End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373945a1bc43700c2a62e17 | 8.2 BACKEND - Query Results Room A | https://trello.com/c/BPVB7itW/78-82-backend-query-results-room-a |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T09:33:15.066Z | 63739497c66e9803912c48cb | Back End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637394691affa403bb95810e | 8.3 BACKEND - Query Results Room B | https://trello.com/c/miSAEW77/79-83-backend-query-results-room-b |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T09:33:09.371Z | 63739497c66e9803912c48cb | Back End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637394b70f622301b0329df7 | 8.4 BACKEND - Query Results Room C | https://trello.com/c/EuWvh0ZZ/80-84-backend-query-results-room-c |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T09:33:03.841Z | 63739497c66e9803912c48cb | Back End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637394c3dcd34a01e6e880cc | 8.5 BACKEND - Query Results Room D | https://trello.com/c/kwxeZhw2/81-85-backend-query-results-room-d |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T09:32:57.198Z | 63739497c66e9803912c48cb | Back End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6392666c530f8405c26ee854 | BACKEND - booking query | https://trello.com/c/DutcZefl/96-backend-booking-query |  |  | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-08T22:38:06.765Z | 63739497c66e9803912c48cb | Back End (To-Do) | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
6357317b9f96c300d7c24e64 | Design & Research | https://trello.com/c/11bwalH0/33-design-research | All design and product research tasks should go here. |  |  |  | 1 | https://trello.com/1/cards/6357317b9f96c300d7c24e64/attachments/6357318e9e638a0191690edf/download/Design.png | 0 | 0 | 0 | 0 | 2022-10-25T00:45:38.788Z | 6357314a51ea750030ef7ed9 | Design | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634d74861382cb00a145e517 | Research calendar date range picker implementation | https://trello.com/c/Bafn8ZS9/13-research-calendar-date-range-picker-implementation | We would like to implement modern ui/ux calendars for hotel bookings (check-in and check-out dates) using HTML5, JavaScript or CSS3 |  | chimuanyaibecheozor1 | 2022-10-21T21:39:00.000Z | 0 |  | 0 | 0 | 0 | 1 | 2022-10-25T01:10:02.208Z | 6357314a51ea750030ef7ed9 | Design | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
635972cdca28f5036cc56edc | Acessibility Research | https://trello.com/c/YQDD0DsP/46-acessibility-research | Research on web accessibilty technology and how it influences people with disability. Outcome: Learn about WCAG (web content accessibility guidelines) |  |  |  | 2 | https://trello.com/1/cards/635972cdca28f5036cc56edc/attachments/635973b8142987009385e754/download/Example_W.pdf, https://trello.com/1/cards/635972cdca28f5036cc56edc/attachments/635975f91db7c9001e6c980c/download/applsci-11-00368-v3-compressed.pdf | 0 | 0 | 0 | 1 | 2022-10-26T18:04:57.159Z | 6357314a51ea750030ef7ed9 | Design | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
635737efc15b2d017a1b310a | Demo & Sprint Review | https://trello.com/c/7tHVccfb/41-demo-sprint-review | Here we demo our potentially shippable products or deliverables for the sprint and review the way we have worked and reflects on how things could have been done better. |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-11-15T13:56:14.199Z | 635732a9fd3559056792a314 | Current Sprint | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6359724713772a01e723ca09 | Textual Diagram | https://trello.com/c/OsKCuXYF/44-textual-diagram |  |  | chimuanyaibecheozor1, kyokoyamasaki, muhammadhajijamel, rayaanchowdhury2 | 2022-11-02T14:00:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-10-26T18:27:38.889Z | 635732a9fd3559056792a314 | Current Sprint | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
63597252d76f05032e2b4a71 | Sequence Diagram | https://trello.com/c/gSJaXmoq/45-sequence-diagram |  |  | chimuanyaibecheozor1, kyokoyamasaki, muhammadhajijamel, rayaanchowdhury2 | 2022-11-02T14:00:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-10-26T18:27:36.479Z | 635732a9fd3559056792a314 | Current Sprint | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
637395d5d8e7d1058c24428a | A4 User Guide of System | https://trello.com/c/I6Zt6dRR/88-a4-user-guide-of-system |  |  | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T12:09:43.812Z | 635732a9fd3559056792a314 | Current Sprint | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
639325986dbe1702c7e9413d | A4 Team Member Details | https://trello.com/c/Fa0MfKpT/104-a4-team-member-details |  |  | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T12:10:06.610Z | 635732a9fd3559056792a314 | Current Sprint | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634dc2e56318430108a2808f | Invite professors into Trello: | https://trello.com/c/zq4zMHM4/22-invite-professors-into-trello |  |  | muhammadhajijamel |  | 0 |  | 2 | 0 | 0 | 1 | 2022-10-17T21:06:56.314Z | 634dc2e56318430108a2802b | In Progress | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
634dc2e56318430108a2806f | Take a look at Figma and/or Invision | https://trello.com/c/ERezAol8/23-take-a-look-at-figma-and-or-invision |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T21:13:44.308Z | 634dc2e56318430108a2802b | In Progress | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
634dc2e56318430108a28070 | Inquire about payment handling | https://trello.com/c/EqECRRn0/25-inquire-about-payment-handling |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T21:13:25.275Z | 634dc2e56318430108a2802b | In Progress | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
634dc2e56318430108a2806e | Find out how to calendar in Javascript | https://trello.com/c/oc7Zm9Gy/24-find-out-how-to-calendar-in-javascript |  |  | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T21:13:42.048Z | 634dc2e56318430108a2802b | In Progress | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
634dc2f5f2c6f00076755e17 | Find out how to calendar in Javascript | https://trello.com/c/LmhXCrqO/29-find-out-how-to-calendar-in-javascript |  |  | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T21:06:01.370Z | 634dc2e56318430108a2802b | In Progress | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
634d7d1c5672f101f3ba7568 | Demo and Status update on Saturday 22nd | https://trello.com/c/XEVd8nic/21-demo-and-status-update-on-saturday-22nd | Here we demo our potentially shippable products or deliverables for the sprint and review the way we have worked and reflects on how things could have been done better. |  | chimuanyaibecheozor1, kyokoyamasaki, muhammadhajijamel, rayaanchowdhury2 | 2022-10-22T15:30:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-10-24T22:57:29.249Z | 634d7634545e1300a6048e88 | Demo & Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634336353f3b95034661973f | . | https://trello.com/c/2SInyi5U/4-untitled |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-09T20:59:42.841Z | 634330e1f5185f0146e485ff | Coding | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634336b71712a1042d2313ca | . | https://trello.com/c/7ge93RQP/6-untitled |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-09T21:01:53.596Z | 634333a56140c001b713dcf3 | Testing | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634335f64b5a9c0563e61fb8 | Omedetou! | https://trello.com/c/vdnailJq/3-omedetou |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-09T20:58:43.237Z | 634330e1f5185f0146e48600 | Done | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634334b9803cea0024e900cb | Get group approved via email | https://trello.com/c/vgYlgfAv/1-get-group-approved-via-email |  | (orange) |  | 2022-10-12T16:00:00.000Z | 1 | https://learn-eu-central-1-prod-fleet01-xythos.content.blackboardcdn.com/5f47a5775541f/12944597?X-Blackboard-Expiration=1665360000000&X-Blackboard-Signature=vIxQV2KtdPO4NacpDp1VaRYV1q4whWG%2FWpmevPX%2By24%3D&X-Blackboard-Client-Id=131628&response-cache-control=private%2C%20max-age%3D21600&response-content-disposition=inline%3B%20filename%2A%3DUTF-8%27%27groups-v1.pdf&response-content-type=application%2Fpdf&X-Amz-Security-Token=IQoJb3JpZ2luX2VjEIT%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaDGV1LWNlbnRyYWwtMSJIMEYCIQD0A4%2BlfAzUuwUswVemV%2FR6l1bAk6Gp6thFuD7aMODVDAIhAKhXgH5cIOdwSMCbxB7HmnhgzVMGn%2BCu8SW5jppEe4z9KtYECEwQAhoMNjM1NTY3OTI0MTgzIgzyqfP1Fd8r56Jv56UqswQBHiEkbI98bLQXF%2FVze7f3BveN9jqHzmKOPiGmZq4LCPXpRC7AHtiHgRa%2BtpE8SpLqbd51yC5sbuo0XflMlPcHQO8k8GWMYWQCM2TamL2kybPsQC7QPQfDJmG82H%2BNdlAK5jrGra%2F10wKKDm%2BjmBtWJD7BOFDtaUVAvOV5076%2FQc4OToXClxoXwMerxqJW2jUd%2BQKttmEK%2F47xIo08STnFP%2FyD4WKT9ml3yLNJCDoKpSBegEEovY5POJTrKUfU1Zr4lwRPah821%2FdYxYnSDOlX7wkh9W49H5tFAb7jbHcDaQZ1wsUaph2NUOH7Z0t6NVcvBQ4id3qEyAZlH2QezWHE%2F7izKrPx0%2Bgcov%2BFASCmR5Hfy2178gBcj5ZTJyFhQSzGbjtpFGeLWYPOIQp3%2FMARDkziVztyQ6R6ia8C4zM1CCmhhALC3VHHWJBF7Q9gNaPJ3YiOgjxAFIEDpw26mJiQjVeq6G9L4Fxp6rF1L7%2F%2FM%2F2WBtKs%2B0FUoEApRbYOCy5Z8pXphUh%2Beun%2BhXqmyYzSK%2FOmPCpFz7IBQUVOs85AVRdOpS2EahsFMCB1NFwKdTk4WW5tRBrs4YyqBimwo%2F7qvNfzmU2Xl%2F%2BGsYbu2LlOOSmcP%2BaON1%2BKjB6K46F1hAqoYz7Z9wdMijinYBhNO34vo0Y7SG2%2FFi%2BrI%2F8UiumFO2%2BpoqXto%2BI3N%2FHGvDCVtbRNTG8pgDQzX7ggWamWrToga8pdq659lrW74Srjx7qAXa0rcjCqwIyaBjqoASmLtiUQhQhf8i%2BX2Eu1RTv0iWZwVRC58RJ9pA5PvNo4FXr5jXnnuGwBcqS8UZtX1%2BJcjTowl6cdAQx0WDpmgx9aBOnAT2aCBrcxEUPY3Nm5UffCSJJPwk2c82eF8DfvkNvK8vSO4q8%2B%2FUYlWgqK573URrWbI5VtmVSOEQeliScw0%2FQVfSi%2F6V91XRJV8svLDdJFqLV3rYVEsdbTBh6awVZwwU5UuXaYLg%3D%3D&X-Amz-Algorithm=AWS4-HMAC-SHA256&X-Amz-Date=20221009T180000Z&X-Amz-SignedHeaders=host&X-Amz-Expires=21600&X-Amz-Credential=ASIAZH6WM4PL56MSW27A%2F20221009%2Feu-central-1%2Fs3%2Faws4_request&X-Amz-Signature=48408f0cca458dc0310e48bcfc4451ae0e14b63d956fa0e87a3d650e5b867db4 | 0 | 0 | 0 | 0 | 2022-10-16T08:24:46.725Z | 634330e1f5185f0146e48600 | Done | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
634337f0cd2bb801499a5bca | Confirm Account on Trello | https://trello.com/c/OtBOPRhh/7-confirm-account-on-trello | I can make everyone else Admin, accept you, so once you confirm your email with your student email I can add you. |  |  |  | 1 | https://trello.com/1/cards/634337f0cd2bb801499a5bca/attachments/63433834971a6000ede00aa4/download/chrome_SkBePJu4y2.png | 0 | 0 | 0 | 0 | 2022-10-16T08:24:46.785Z | 634330e1f5185f0146e48600 | Done | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634bcc62d26d1c0354fc5888 | Ask Dr. Jeannette if website will be live | https://trello.com/c/e0l3VHWN/9-ask-dr-jeannette-if-website-will-be-live |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T12:14:35.874Z | 634330e1f5185f0146e48600 | Done | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634bcc51d1079500d14e8ac2 | Ask. Dr. Jeannette about Jaejoon Lee ID | https://trello.com/c/P69y3KmS/8-ask-dr-jeannette-about-jaejoon-lee-id |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T12:13:42.583Z | 634330e1f5185f0146e48600 | Done | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634bd902ceca0d01951dd76b | Check for free domain hosts | https://trello.com/c/NZujaSKn/12-check-for-free-domain-hosts |  |  | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T15:39:29.244Z | 634330e1f5185f0146e48600 | Done | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
635737efc15b2d017a1b3169 | Invite professors into Trello: | https://trello.com/c/TyTojEWq/36-invite-professors-into-trello |  |  | muhammadhajijamel |  | 0 |  | 1 | 0 | 0 | 2 | 2022-10-25T01:12:26.413Z | 635737efc15b2d017a1b309b | Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
635737efc15b2d017a1b3134 | Inquire about payment handling | https://trello.com/c/aAIgDhQt/43-inquire-about-payment-handling |  |  |  |  | 0 |  | 1 | 0 | 0 | 1 | 2022-10-25T01:12:30.196Z | 635737efc15b2d017a1b309b | Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
635737efc15b2d017a1b313e | Source free images | https://trello.com/c/lRpVt3aT/40-source-free-images |  |  | kyokoyamasaki, rayaanchowdhury2 | 2022-10-21T21:39:00.000Z | 0 |  | 0 | 0 | 0 | 1 | 2022-10-25T01:12:33.973Z | 635737efc15b2d017a1b309b | Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
635737efc15b2d017a1b3110 | Empathy Map | https://trello.com/c/zIVnWkWG/39-empathy-map |  |  | kyokoyamasaki | 2022-10-24T15:30:00.000Z | 2 | https://trello.com/1/cards/635737efc15b2d017a1b3110/attachments/635737efc15b2d017a1b31f2/download/Empathy_map_for_Emma_%26_John.pptx, https://trello.com/1/cards/635737efc15b2d017a1b3110/attachments/635737efc15b2d017a1b31f4/download/rev.Empathy_map_for_Emma_%26_John.pdf | 0 | 0 | 0 | 0 | 2022-10-25T01:12:36.435Z | 635737efc15b2d017a1b309b | Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
635737efc15b2d017a1b3116 | Personas | https://trello.com/c/suCyfTVF/38-personas |  |  | muhammadhajijamel | 2022-10-23T21:39:00.000Z | 2 | https://trello.com/1/cards/635737efc15b2d017a1b3116/attachments/635737efc15b2d017a1b31e0/download/Web_app_persona1-01.png, https://trello.com/1/cards/635737efc15b2d017a1b3116/attachments/635737efc15b2d017a1b31e9/download/Web_app_persona1-02.png | 4 | 0 | 0 | 0 | 2022-10-25T01:12:39.655Z | 635737efc15b2d017a1b309b | Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
635737efc15b2d017a1b3111 | MOSCOW | https://trello.com/c/XBUuJfOR/42-moscow |  |  | kyokoyamasaki, rayaanchowdhury2 | 2022-10-21T21:39:00.000Z | 1 | https://trello.com/1/cards/635737efc15b2d017a1b3111/attachments/635737efc15b2d017a1b31fd/download/MoSCoW.pptx | 0 | 0 | 0 | 0 | 2022-10-25T01:12:41.844Z | 635737efc15b2d017a1b309b | Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
635737efc15b2d017a1b3115 | UML Diagrams | https://trello.com/c/ulC5ch1M/37-uml-diagrams |  |  | chimuanyaibecheozor1, muhammadhajijamel | 2022-10-21T21:39:00.000Z | 1 | https://trello.com/1/cards/635737efc15b2d017a1b3115/attachments/635737efc15b2d017a1b3204/download/HOTEL_USE_CASE.png | 0 | 0 | 0 | 0 | 2022-10-25T01:12:45.299Z | 635737efc15b2d017a1b309b | Sprint Review | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
6357357863a863007741aa91 | Demo & Sprint Review | https://trello.com/c/nhMjn5PK/34-demo-sprint-review | Here we demo our potentially shippable products or deliverables for the sprint and review the way we have worked and reflects on how things could have been done better. |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-08T22:36:54.061Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634334c798bb790206de40cd | Invite professors into Trello: | https://trello.com/c/7UiGvJdz/2-invite-professors-into-trello |  |  | muhammadhajijamel |  | 0 |  | 1 | 1 | 0 | 2 | 2022-12-08T22:37:46.145Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634dc2f5f2c6f00076755e13 | Inquire about payment handling | https://trello.com/c/LBffWlJ3/28-inquire-about-payment-handling |  |  |  |  | 0 |  | 1 | 1 | 0 | 1 | 2022-12-08T22:47:48.575Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634bcc791461e200ed4967db | Take a look at figma/Invision | https://trello.com/c/fgPUbzVJ/10-take-a-look-at-figma-invision | This tasks involves taking a deep look into Invision, a UI design tools that lets us collaborate, create, design, and prototype mobile and web interfaces. |  | chimuanyaibecheozor1, muhammadhajijamel | 2022-10-25T15:30:00.000Z | 0 |  | 0 | 0 | 0 | 0 | 2022-12-08T22:37:25.782Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
6367335902f63d0102fee582 | Assignment Specification | https://trello.com/c/nJG91cW7/53-assignment-specification |  |  |  |  | 1 | https://trello.com/1/cards/6367335902f63d0102fee582/attachments/6367337efc6e9c00bb8e8e74/download/CMP-7003A-002-2022-23-checked.pdf | 0 | 0 | 0 | 0 | 2022-12-08T22:37:16.589Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
637eb5f99874b101bea93d35 | Set up codebase on github and share access | https://trello.com/c/lnWa4ghl/95-set-up-codebase-on-github-and-share-access |  |  | chimuanyaibecheozor1 | 2022-11-16T00:05:00.000Z | 0 |  | 0 | 0 | 0 | 1 | 2022-12-08T22:49:58.348Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
6392697c3705ef0547725371 | Navbar Design CSS | https://trello.com/c/1nnQz8Rm/101-navbar-design-css |  | HTML&CSS (red_light) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:55:48.169Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63926974020b0a00a0519f0e | Footer Design CSS | https://trello.com/c/AFUVgZRe/100-footer-design-css |  | HTML&CSS (red_light) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:55:40.618Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637388d56c259800d71b9560 | 4.1 Payment Form (Customer Details) | https://trello.com/c/1bBRop5E/69-41-payment-form-customer-details |  |  | chimuanyaibecheozor1 |  | 0 |  | 3 | 3 | 0 | 1 | 2022-12-09T12:36:01.188Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637388efab3cc2028cfab0d6 | 4.3 Front end - Payment Confirmed | https://trello.com/c/dhYXkR8t/71-43-front-end-payment-confirmed |  |  | chimuanyaibecheozor1 | 2022-11-21T00:05:00.000Z | 0 |  | 0 | 0 | 0 | 1 | 2022-12-09T12:36:33.090Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | TRUE
639268334f697e01eeafac8b | Payment Form JS | https://trello.com/c/UUHgQ9PM/97-payment-form-js | client side javaScript to handle payment form submission to the nxt page (confirmation page) | JS&Nodejs (lime) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 1 | 2022-12-09T12:37:57.205Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6392684a2166fa00c9dea906 | Payment Confirmation Form JS | https://trello.com/c/JkjJEOEL/98-payment-confirmation-form-js | client side javaScript to handle confirmation and room booking payment | JS&Nodejs (lime) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 1 | 2022-12-09T12:38:27.064Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6392685a3fd8e301398a8e01 | Payment confirmed JS | https://trello.com/c/vvAtQ69L/99-payment-confirmed-js | client side javaScript to show booking payment information and booking number | JS&Nodejs (lime) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 1 | 2022-12-09T12:39:13.777Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
634dc2f6f2c6f00076755e4b | Invite professors into Trello: | https://trello.com/c/41wReFdc/26-invite-professors-into-trello |  |  | muhammadhajijamel |  | 0 |  | 2 | 0 | 0 | 1 | 2022-10-17T21:06:28.270Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
634dc2f5f2c6f00076755e16 | Take a look at Figma and/or Invision | https://trello.com/c/A3O95Nod/27-take-a-look-at-figma-and-or-invision |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-17T21:06:38.360Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | TRUE |  | FALSE
637388e80243ce021ac62ce7 | 4.2 Front - end Payment Confirmation | https://trello.com/c/bKLvuNNG/70-42-front-end-payment-confirmation |  | HTML&CSS (red_light) | chimuanyaibecheozor1 |  | 0 |  | 2 | 2 | 0 | 0 | 2022-12-09T08:50:23.578Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
639273add5e3fc00b3a7cb22 | Fix index page css bug | https://trello.com/c/mU0G0QSU/102-fix-index-page-css-bug |  | HTML&CSS (red_light) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T08:50:13.472Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63928de7e6436400d726b563 | Index page contact form processing | https://trello.com/c/ndGNXqCc/103-index-page-contact-form-processing |  | JS&Nodejs (lime) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:53:52.393Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63932864a44b3603ed1ca76a | Fix page redirect bug | https://trello.com/c/pHUmuvSm/105-fix-page-redirect-bug |  |  | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 1 | 2022-12-09T12:34:54.973Z | 634dc2f5f2c6f00076755dd6 | Completed | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63573709e91ac7015d160ef1 | Impl | https://trello.com/c/LpIEtixc/35-impl |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 2022-10-25T01:08:25.224Z | 635736c3b19f4502227deb2f | Code | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373844a821f6502672e2eab | 1 HTML Index | https://trello.com/c/NlaNp03v/54-1-html-index |  | HTML&CSS (red_light) | muhammadhajijamel |  | 0 |  | 0 | 0 | 0 | 1 | 2022-12-09T11:47:54.948Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637384789c3b73060b2872a5 | 1.1.1 HTML Index>Pop-Up Room Type A | https://trello.com/c/N1ovrWDS/55-111-html-indexpop-up-room-type-a | Update the pictures to match room types | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 5 | 0 | 0 | 0 | 2022-12-09T11:48:00.909Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373847a60d24f00364f25b1 | 1.1.2 HTML Index>Pop-Up Room Type B | https://trello.com/c/IkGiiGx8/56-112-html-indexpop-up-room-type-b |  | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:49:44.127Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373848b37167800c9f55a6f | 1.1.3 HTML Index>Pop-Up Room Type C | https://trello.com/c/GqeI14XZ/57-113-html-indexpop-up-room-type-c |  | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:49:49.885Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373848ea6093f0067af4f84 | 1.1.4 HTML Index>Pop-Up Room Type D | https://trello.com/c/OCBK4K2k/58-114-html-indexpop-up-room-type-d |  | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:49:52.677Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637384a9a9d8f101b6c2d02b | 1.2.1 HTML Index>Pop-Up Facilities 1 | https://trello.com/c/dvGFRi2H/59-121-html-indexpop-up-facilities-1 |  | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:50:00.976Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637384f1dacb76067b565acc | 1.2.2 HTML Index>Pop-Up Facilities 2 | https://trello.com/c/bFMbmwBQ/60-122-html-indexpop-up-facilities-2 |  | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:47:58.149Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63738508e6c7dd0133308352 | 1.2.3 HTML Index>Pop-Up Facilities 3 | https://trello.com/c/bQziaXYy/61-123-html-indexpop-up-facilities-3 |  | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:53:24.312Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373854032c73801e91d51a5 | 1.2.4 HTML Index>Pop-Up Facilities 4 | https://trello.com/c/bWB4hATE/62-124-html-indexpop-up-facilities-4 |  | HTML&CSS (red_light) | rayaanchowdhury2 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:50:16.043Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373866d50c4a201fe2372a2 | 2. Query Results ALL | https://trello.com/c/eHPaI84P/63-2-query-results-all |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 5 | 4 | 0 | 0 | 2022-12-09T11:48:02.591Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63738681475e9d0016220e5b | 3.1 Query Results Room A | https://trello.com/c/tAC4HYbg/64-31-query-results-room-a |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:48:04.635Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373880a475e131073b1e1ea | 3.2 Query Results Room B | https://trello.com/c/lovv5wJt/66-32-query-results-room-b |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:48:06.726Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373885837c8f200d74cb315 | 3.3 Query Results Room C | https://trello.com/c/aKs0nfTx/67-33-query-results-room-c |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:48:09.067Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63738871a8f2bf04d596486b | 3.4 Query Results Room D | https://trello.com/c/DfZp3fFX/68-34-query-results-room-d |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:48:11.086Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373893b33363d03bf5e6b9f | 5.1 My Bookings Page | https://trello.com/c/WsccnaZk/72-51-my-bookings-page |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:48:13.530Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373943a14e0220099764803 | 8.1 BACKEND - Query Results ALL | https://trello.com/c/pmNDUyla/77-81-backend-query-results-all |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:52:00.975Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637395078046ac010d780313 | 9.1 BACKEND - Payment Form | https://trello.com/c/3zKFKYj3/82-91-backend-payment-form |  | JS&Nodejs (lime) | chimuanyaibecheozor1 |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:53:02.250Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63739511d200ff002f406fcb | 10.1 BACKEND - My Bookings | https://trello.com/c/148eClwX/83-101-backend-my-bookings |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:52:56.113Z | 63932062bcd3e2019dfb9a75 | Completed-for customer page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373897665f790051ca74da8 | 6.1 RECEPTION - Search Page | https://trello.com/c/lcQFqBu6/73-61-reception-search-page |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:49:23.590Z | 639320a388b9ec02af90ac14 | Completed-for reception page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637389805716ea00b42b0911 | 6.2 RECEPTION - Query Results | https://trello.com/c/VhfVsowQ/74-62-reception-query-results |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:49:25.369Z | 639320a388b9ec02af90ac14 | Completed-for reception page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373899f5611fa0c281a1274 | 6.3 RECEPTION - Booking Details | https://trello.com/c/e0WCqdUd/75-63-reception-booking-details |  | HTML&CSS (red_light) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:49:27.027Z | 639320a388b9ec02af90ac14 | Completed-for reception page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373951e8d8875017f4ea591 | 11.1 BACKEND - Reception Search | https://trello.com/c/13JbkoJa/84-111-backend-reception-search |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:52:30.658Z | 639320a388b9ec02af90ac14 | Completed-for reception page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
637395307b6c5303fc84d5a4 | 11.2 BACKEND - Reception Query Results | https://trello.com/c/rXaOYu2I/85-112-backend-reception-query-results |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:52:34.427Z | 639320a388b9ec02af90ac14 | Completed-for reception page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
6373957421264e00234384f3 | 11.3 BACKEND - Reception - booking Details | https://trello.com/c/5SoM5A4N/86-113-backend-reception-booking-details |  | JS&Nodejs (lime) | kyokoyamasaki |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:52:39.047Z | 639320a388b9ec02af90ac14 | Completed-for reception page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63738dafebe8b4001de93d0d | 7.1 CLEANER - Room Clean Status Page | https://trello.com/c/d3f1gV3B/76-71-cleaner-room-clean-status-page |  | HTML&CSS (red_light) | muhammadhajijamel |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:50:08.564Z | 639320b22fe8c900d7981987 | Completed-for cleaner page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE
63739585621cab04b36cfbd1 | 12.1 BACKEND Cleaner status | https://trello.com/c/wmT8D52U/87-121-backend-cleaner-status |  | JS&Nodejs (lime) | muhammadhajijamel |  | 0 |  | 0 | 0 | 0 | 0 | 2022-12-09T11:52:46.322Z | 639320b22fe8c900d7981987 | Completed-for cleaner page | 634330e1f5185f0146e485f7 | Web Development Assignment | FALSE |  | FALSE